## Daily Status Report
Date | Day | Task Performed | Module | Cases Executed | Bugs Found | Remarks
01-Jun-2026 | Day 1 | Environment setup, application walkthrough, test plan drafting | Login, Signup | 0 | 0 | Kick-off day; no execution, planning only
02-Jun-2026 | Day 2 | Test scenario & test case design for authentication modules | Login, Signup, Email Verification | 0 | 0 | Test case design in progress
03-Jun-2026 | Day 3 | Test case execution - Authentication modules | Login, Signup, Forgot Password | 22 | 3 | 3 defects logged (BUG_002, BUG_003, BUG_004)
|  | TOTAL |  | 22 | 3